## Sheet1
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
KA1 | Research Docker | General Application | 1 | Create Dev Environment files | KA | 3 | 3 | Nick 60%/Tyler 40%
KA2 | Research JavaScript | General Application | 1 | Learn Basic Syntax + Operations | KA | 3 | 3 | Heath/Tristan/Nick/Kass/Tyler (20% each)
KA3 | Research NodeJS | General Application | 1 | Familiarization | KA | 3 | 3 | Heath/Tyler (50% each)
KA4 | Research GitHub | General Application | 1 | Practice Pull/Add/Commit/Push Cycle | KA | 2 | 2 | Tristan/Kass/Nick/Heath/Tyler (20% each)
KA5 | Research React | General Application | 1 | Familiarization | KA | 3 | 3 | Tyler/Kass (50% each)