## Sheet1
ID | User Story | Sprint Number | Story Priority | Story Status | Story Points
s1 | As a user I want to be able to browse public recipes by title so that I can expand my cooking knowledge. | 5 | M | T | 4
s2 | As a user I want to be able to search recipes by title so that I can find a specific recipe I already have in mind. | 5 | M | T | 3
s3 | As a user I want to be able to filter my search for public recipes based on ingredients because I want recipes for what is in my fridge. | TBD | M | W | 3
s4 | As a user I want to be able to filter my search for public recipes based on tools because I only want recipes that I have the tools to make. | TBD | M | W | 3
s5 | As a registered user I want to browse my private collection of recipes so that I don't have to waste time scrolling over public recipes that I do not want to take a chance with. | TBD | H | W | 3
s6 | As a registered user I want to be able to follow other registered users so that I can see when they post a new public recipe. | TBD | L | W | 3
s7 | As a registered user I want to be able to browse recipes by a specific user so that I can see all the recipes they have posted publicly. | TBD | L | W | 4
c1 | As a registered user I want to be able to create a new recipe page so that I can store a recipe electronically. | 2 | H | IP | 4
c2 | As a registered user I want to be able to toggle if my recipes are public or private so that I can choose who can see them. | TBD | H | W | 3
c3 | As a registered user I want to be able to upload pictures of the dish if I choose, so that people can see how wonderful the dish looks. | 5 | M | IP | 3
c4 | As a registered user I want to be able to display the ingredients of my recipe so that I or another user will know what ingredients are needed to cook it. | 5 | H | T | 3
c5 | As a registered user I want to be able to display the units of a specific ingredient so that readers can know what measuring instruments to use. | 5 | H | T | 3
c6 | As a registered user I want to display nutritional information of a recipe so that I can show that the dish is healthy to people who I might be sharing with. | TBD | L | W | 3
c7 | As a registered user I want to tag kitchen equipment required for my recipe so that it will show up in a search when a user whitelists for said equipment. | TBD | M | W | 4
c8 | As a registered user I want to be able to tag allergies to a recipe so that someone on a specific diet will be able to easily blacklist or whitelist it in searches. | TBD | L | W | 4
c9 | As a registered user I want to be able to tag my recipe with its required ingredients so that it will show up in a search when a user whitelists for the ingredients. | 5 | M | IP | 4
a1 | As a user I want to register an account on the platform so that I can post recipes for public or private use. | TBD | H | W | 4
a2 | As a registered user I want to log in to my account so that I can use features exclusive to registered users. | TBD | H | IP | 4
o1 | As a registered user I want to be able to share recipes with people outside the platform so that I can share my family recipes. | 4 | L | D | 4
o2 | As a user I want to be able to get step-by-step prompts when cooking so that I don't have to fumble with my electronics when I am cooking. | TBD | L | W | 6
KA1 | Research Docker | 1 | H | D | 3
KA2 | Research JavaScript | 1 | H | D | 3
KA3 | Research NodeJS | 1 | M | D | 3
KA4 | Research GitHub | 1 | H | D | 2
KA5 | Research React | 1 | H | D | 3
KA6 | Research Flux architecture | 2 | H | D | 4
KA7 | Research SQL & NonSQL databases | 3 | H | D | 3
KA8 | Research Flask | 4 | H | IP | 4
FE1 | FrontEnd Development Setup | 2 | H | D | 4
BE1 | BackEnd Development Setup | 3 | H | D | 3
FE1 | FrontEnd Styling | 5 | M | IP | 3