## Sprint 1
| User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
KA1 | Research Docker | General Application | 1 | Create Dev Environment files | KA | 3 | 3 | Nick 60%/Tyler 40%
KA2 | Research JavaScript | General Application | 1 | Learn Basic Syntax + Operations | KA | 3 | 3 | Heath/Tristan/Nick/Kass/Tyler (20% each)
KA3 | Research NodeJS | General Application | 1 | Familiarization | KA | 3 | 3 | Heath/Tyler (50% each)
KA4 | Research GitHub | General Application | 1 | Practice Pull/Add/Commit/Push Cycle | KA | 2 | 2 | Tristan/Kass/Nick/Heath/Tyler (20% each)
KA5 | Research React | General Application | 1 | Familiarization | KA | 3 | 3 | Tyler/Kass (50% each)

## Sprint 2
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
KA6 | Research Flux | General Application | 2 | Familiarization | KA | 4 | 4 | Heath/Kass/Nick/Tyler/Tristan (20% each)
KA5 | Research React | General Application | 2 | Familiarization | KA | 3 | 3 | Tyler/Nick (50% each)
FE1 | Frontend Development | General Application | 2 | Initial UI development | F | 3 | 3 | Tyler 50%/Nick 50%
C1 | User Story: c1 | Recipe Creation | 2 | Initial Development | F | 4 | 0 | Heath/Kass/Nick/Tyler/Tristan (20% each)

## Sprint 3
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
KA3 | Research NodeJS | General Application | 3 | Research how to connect React w/ NodeJS | KA | 3 | 3 | Tristan / Heath / Tyler (30/30/30)
KA5 | Research React | General Application | 3 | Familiarization + expirimentation | KA | 3 | 3 | Tristan / Kass / Heath / Tyler (25/25/25/25)
KA6 | Research Flux | General Application | 3 | Research how to Flux Architecture is related to our code implementation | KA | 4 | 4 | Heath(100)
KA7 | Research SQL & NonSQL databases | General Application | 3 | Familiarization & deciding which database structure is best for web app | KA | 3 | 3 | Nick / Tyler (50/50)
FE1 | Frontend Development | General Application | 3 | Adding design elements to Frontend & Adding limited functionality | F | 3 | 3 | Tristan (100)
BE1 | BackEnd Development | General Application | 3 | Establishing backend framework + updating development environment | F | 3 | 3 | Heath / Tyler (50/50)
C1 | User Story: c1 | Recipe Creation | 3 | Initial Development | F | 4 | 0

## Sprint 4
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
KA3 | Research NodeJS | General Application | 4 | Connect with Express | KA | 3 | 3 | Tristan, Tyler, Heath (equal)
KA5 | Research React | General Application | 4 | Familiarization + experimentation | KA | 3 | 3 | Tristan, Kass (equal)
KA7 | Research Flask | General Application | 4 | Learn enough to figure out if it can be used instead of Node | KA | 4 | 4 | Nick, Heath (60/40)
FE1 | Frontend Development | General Application | 4 | Show images and render a recipe | F | 3 | 3 | Nick, Tristan, Heath (equal)
BE1 | BackEnd Development | General Application | 4 | Connect the backend to the database | F | 3 | 3 | Nick (100)
C3 | User Story | Recipe Creation | 4 | Show images from the database | F | 4 | 4 | Nick (100)